## Sheet1
Task	Hours

Development of an electronic schematic and ordering parts for testing	10
Design of the module 3D CAD	2
Design of the chassis 3D CAD	3
Design of the light box 3D CAD	3
Design of the frame 3D CAD	2
Revision and correction of the design and ordering parts	5
Testing schematic on breadboard	4
Design of the module EDA	2
Design of the chassis EDA	3
Design of the light box EDA	2
Order PCB from JLCPCB	1
Make threads and finish laser cut parts	5
Assembly and soldering of the PCB	5
Assembly of the chassis and modules for inspection	5
Assembly of the light box	5
Correction of the PCB and order of the second version	4
Correction of the enclosure and order of the second version	3
Assembly and soldering of the PCB	5
Assembly of the whole piece	5

	74

	Total		2960

## Sheet2
Item	Quantity	Cost	Link

Old TV / Monitor

Laser cut parts

Electronic components

Laser Cutter

Wire stripper

Watch

Sweater